## 工作表1
[6 empty] | October | [16 empty] | November | [29 empty] | December
Tasks | Start | End | member(s) allocated |  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Planning | 2022-10-13 | 2022-10-15
agree on the product chose and inform staff |  |  | Kwan Ho | Nixon | Andrew | bar: October 15 S to October 16 S
interview some events management students to prepare information needed for the next phase |  |  |  |  | Andrew | bar: October 15 S
Requirements | 2022-10-16 | 2022-10-22
make a Gantt Chart to write down the project plan and the contribution of members |  |  | Kwan Ho | bar: October 17 M
risk assessment |  |  | Kwan Ho | Nixon | Andrew | bar: October 17 M to October 22 S
to sort the requirements gathered in Moscow |  |  | Kwan Ho | Nixon | Andrew | bar: October 17 M to October 22 S
Design | 2022-10-23 | 2022-10-26
change the requirement to be focused on project instead of on product after meeting project adviser |  |  |  | Nixon | bar: October 23 S to October 25 T
to design user interface diagram |  |  |  |  | Andrew | bar: October 26 W to November 26 S
to design Data Flow Diagram |  |  | Kwan Ho | bar: October 26 W to November 11 F
Implementation | 2022-11-27 | 2022-12-10
project control management - Trello |  |  |  | Nixon | bar: November 27 S to December 10 S
website pages development |  |  | Kwan Ho | bar: November 27 S to December 10 S
Testing | 2022-12-11 | 2022-12-17
Report(Implementation Information) |  |  |  | Nixon | bar: December 11 S to December 15 T
Report(Testing) |  |  | Kwan Ho | bar: December 11 S to December 15 T
Report(Design and Explanation) |  |  | Kwan Ho
Report(Reqirement Specification) |  |  |  | Nixon
Delivery | 2022-12-18 | bar: December 16 F